## Daily Gantt Chart Template
Gantt Chart
Career Readiness and Internship Study | [5 empty] | Cheyenne, Jackie, Megan, Juan, Louis
PROJECT NAME | [5 empty] | NAME
Task Assignments | Task Name | Start Date | End Date | Duration (In Days) | 2025-09-09 | 2025-09-12 | 2025-09-18 | 2025-09-25 | 2025-10-02 | 2025-10-05 | 2025-10-20 | 2025-11-06 | 2025-11-18 | 2025-12-02 | 2025-12-04
Cheyenne | Contact Career Services, Secure attendance Data | 2025-09-09 | 2025-09-12 | 3 | bar: 2025-09-09 to 2025-09-12
Cheyenne | Design/distribute student survey | 2025-09-12 | 2025-09-18 | 7 | bar: 2025-09-12 to 2025-09-18
Juan/Cheyenne | Clean and Organize raw data into Excel | 2025-09-18 | 2025-09-25 | 8 | bar: 2025-09-18 to 2025-09-25
Everyone | Use Excel for Decriptive statistics | 2025-09-25 | 2025-10-02 | 8 | bar: 2025-09-25 to 2025-10-02
Juan/Louis | Create charts/Tables | 2025-10-02 | 2025-10-05 | 4 | bar: 2025-10-02 to 2025-10-05
Megan/Louis | Identify trends | 2025-10-05 | 2025-10-20 | 16 | bar: 2025-10-05 to 2025-10-20
Cheyenne | Translate findings into recommendations | 2025-10-20 | 2025-11-06 | 18 | bar: 2025-10-20 to 2025-11-06
Cheyenne | Draft written report | 2025-11-06 | 2025-11-18 | 13 | bar: 2025-11-06 to 2025-11-18
Jackie | Proofread and format report | 2025-11-06 | 2025-11-18 | 13 | bar: 2025-11-06 to 2025-11-18
Jackie | Create Powerpoint/Slides | 2025-11-06 | 2025-11-18 | 13 | bar: 2025-11-06 to 2025-11-18
Cheyenne | Assign speakers/ finalize presentation | 2025-11-18 | 2025-11-18 | 1 | bar: 2025-11-18
All | Presentation | 2025-12-02 | 2025-12-04 | 3 | bar: 2025-12-02 to 2025-12-04
Remarks:
We plan to finish presentation and all project tasks by November 18th.

## ©
© TemplateLab.com