## Sheet1
Project Name: Pulse App: Elderly Health
Project Start Date: Sep. 30, 2024
Project Timelime: 5 Weeks
Project End Date: Dec. 10, 2024
Project Manager: Cheyenne Conner
|  | Week1 | Week 2 | Week 3 | Week 4 | Week 5
Critical Tasks: | Pulse App Design (1) | 1
| Prototyping (2) |  | 2
| Testing (3) |  |  | 3
| Rollout Testing (4) |  |  |  | 4
| App Completion (5) |  |  |  |  | 5
Float Tasks: | Subtask 1.1 Designing App | 1
| Subtask 1.1 Designing Wireframes | 1
| Subtask 2.1 Design Prototype |  | 2
| Subtask 2.2 Use software to build prototype |  | 2
| Subtask 3.1 Test the app |  |  | 3
| Subtask 3.2 Debug any Error |  |  | 3
| Subtask 4.1 Do a soft launch |  |  |  | 4
| Subtask 4.2 Improve app based on feedback |  |  |  | 4
| Subtask 5.1 Launch and present final app |  |  |  |  | 5